## Slide 1
IAS 2019 | July 2019
2025 AIDS Targets: Next Steps
Jose A. Izazola
UNAIDS

## Slide 2: Steps
  Update inventory of services with proven impact in the HIV response
  Propose targets for 2025 to meet existing impact goal for 2030
  Estimate impact on incidence and mortality
  Unit costs for service delivery including integrated service delivery
  Estimate resource needs
  Consider potential long-term impact of future technologies (e.g. vaccines for HIV and TB, injectable ART, etc)

## Slide 3
2025 programmatic targets and 2020‒2030 resource needs and impact estimates
Progress up to date
May
2018
January
2019
July
2019
SC
creation
SC
October
SC
(Virtual)
July
Country ICs
Preparation
Target Setting, Impact Estimation
Q4-2018:
Testing and Treatment
Q1-2019:
Primary Prevention
Q2-2019:
Enablers: social and programme
Technical consultation meetings
Bridging by SC members
Dissemination
IAS 2019
Modelling group interacting with TGs
Q2-3 2019: PMTCT
Brief to stake holders

## Slide 4
2025 programmatic targets and 2020‒2030 resource needs and impact estimates
January
2020
January
2021
SC
Sept
SC
Sept
SC &
TWGs End
Country ICs / NSPs
Update / fine turning / Validation Country Ownership
Q1-2020:
Costs and Resources
Q4-2019:
Integration
Q2-2020: Longer term technologies
Technical consultation meetings
Dissemination
Modelling group interacting with TGs
Resource Needs Estimation
Impact Estimation
October
2019
Online inputs
Webinars CSO
Government
GVA missions
IAS
ICASA
Consultations
Brief to stake holders
https://www.unaids.org/en/topics/2025_target_setting

## Slide 5
2025 programmatic targets and 2020‒2030 resource needs and impact estimates
Dissemination and use of results
Peer reviewed paper
SG report
HLM
UNAIDS strategy
September
2020
January
2021
July
2021
SC
Sept
SC &
TWGs End
PCB
WAD Report
Final Results
Brief to stake holders

## Slide 6: Expected use of results
National target setting and strategies (NSPs)
2021 UN High Level Meeting Political Declaration (date TBC)
GFATM 2023-2026 strategy
PEPFAR strategy
UNAIDS 2022-2026 Strategy

## Slide 7: Thank you!